DEPARTMENT OF VETERANS AFFAIRS

RECOVERY ACT PROGRAM-SPECIFIC PLAN

VETERANS BENEFITS ADMINISTRATION

SUPPORT OF VETERANS ECONOMIC RECOVERY PAYMENTS

JUNE 2010

TABLE OF CONTENTS

1.  Funding Table	3

2.  Objectives	3

3.  Activities	3

4.  Characteristics	4

5.  Delivery Schedule	5

6.  Environmental Review Compliance	5

7.  Measures	5

8.  Monitoring/Evaluation	6

9.  Transparency	6

10.  Accountability	6

11.  Barriers to Effective Implementation	6

12.  Federal Infrastructure Investments	6

Appendix	7

General Operating Expenses – Support of Veteran Economic Recovery Payments Funding Table	7

Table 1A – Account Summary	7

Table 1B – Obligations/Gross Outlays – January 2009 through December 2010	7

Compensation and Pensions Recovery Act Funding Table	8

Table 2A – Account Summary	8

Table 2B – Obligations/Gross Outlays – January through December 2009	8

Information Technology – Support of Veteran Economic Recovery Payments Funding Table	9

Table 3A – Account Summary	9

Table 3B – Obligations/Gross Outlays – January 2009 through December 2010	9

1.  Funding Table

A full funding description is provided in the Appendix.

# 2.  Objectives

The American Recovery and Reinvestment Act of 2009 (ARRA or Recovery Act) provides an estimated $700 million for one-time $250 economic recovery payments to eligible Veterans, their survivors, and dependents to help mitigate the effects of the current economy.  The ARRA also provides $7.1 million to fund administrative costs, plus an additional $100,000 in information technology costs associated with the one-time benefit payments.  Because VA mass mailings had minimal impact on incoming telephone call volume, VA did not require the contract call center (previously estimated to be approximately $5 million) to handle the $250 one-time payment telephone inquiries.  Existing VA telephone call agents handled the increased telephone call volume.

To be eligible for the $250 payment, VA beneficiaries must have received compensation, pension, Dependency and Indemnity Compensation (DIC), or spina bifida benefits at any time between November 2008 and January 2009.  Also, beneficiaries must reside within the United States or Puerto Rico, Guam, Northern Mariana Islands, American Samoa, or the U.S. Virgin Islands.  No application was necessary.  VA used its existing payment records to determine eligibility for the $250 payment.

Beneficiaries received their payments the same way they receive their monthly VA benefits (either by direct deposit or mail).  VA informed beneficiaries and the public when releasing the payments.  Payments were not countable in determining eligibility for VA pension or parents’ DIC.   The law allows one $250 payment per individual.  The payments are tax-free.  VA beneficiaries who also receive benefits from the Social Security Administration or Railroad Retirement Board were paid through those agencies and therefore did not receive the payment from VA.

These efforts correspond with Integrated Objective 1: Make it easier for Veterans and their families to receive the right benefits, meeting their expectations for quality, timeliness, and responsiveness.  In addition, these efforts correspond with Integrated Strategy B: Develop a range of effective delivery methods that are convenient to Veterans and their families.

# 3.  Activities

In addition to disbursing the payments, VA will continue to conduct necessary administrative activities.  Prior to payments going out, VA issued letters advising beneficiaries of the impending one-time $250 payments.  VA also modified existing information technology systems to accommodate the new Treasury account established to hold funds for the payments.  A matching process was conducted with other paying agencies to identify recipients to be paid by VA specifically.  In the event of returned or disputed payments, or if a beneficiary did not receive a payment, VA took the appropriate action to ensure proper payments are issued.   VA performed a full risk assessment for economic recovery payments, which was discussed in the 2009 Performance and Accountability Report.  The chart below breaks out funding for these administrative activities.

| American Recovery and Reinvestment Act Funding Administrative Costs for One-time $250 Payments* |
| --- |
| (dollars in thousands) |
|  | 2009 | 2010 | Total Obligations |
| Total FTE Levels | 3 | 3 |  |
| Obligations |  |  |  |
| Payroll | $162 | $168 | $330 |
| Non-Payroll | $767 | $0 | $767 |
| Total Obligation | $929 | $168 | $1,097 |

* Reflects reduction of previously estimated costs for a call center and a reduced level of administrative work hours than previously expected.

| American Recovery and Reinvestment Act Funding Information Technology Costs for One-time $250 Payments (VETSNET) Q3 FY 2009 (dollars in thousands) |
| --- |
| Funding Requirement | Cost | Description |
| Modifications to existing C&P payment application | $100 | Modifications to existing application in the Veterans Service Network (VETSNET), VA's primary Compensation and Pension (C&P) payment system. |
| VETSNET Subtotal | $100* |  |

# *$100k is the ARRA appropriation amount.  Actual funds spent in 2009 were $243K ($100K ARRA, $143K OI&T).

# 4.  Characteristics

The financial award is $250 in direct payment to eligible Veterans, their survivors, and dependents.  Since the inception of the recovery payment program in June 2009 through April 2010, VA released to beneficiaries more than 1.888 million payments, totaling more than $472 million.  VA anticipates making an additional 31,000 payments, totaling approximately $7.75 million.

$1.2 million is estimated for Federal in-house activities, including $1.1 million to administer payments and $100,000 to modify IT systems to generate payments.

# 5.  Delivery Schedule

VA issued the initial one-time $250 payments and completed all necessary IT modifications by June 2009.  Disbursement of initial payments was followed by auditing and risk assessment for improper payments.  Any returned or disputed payments will be resolved as quickly as possible with all activity completed by December 2010.

# 6.  Environmental Review Compliance

Not applicable

# 7.  Measures

VBA will use the following performance measure to assess the impact of the ARRA funding.

Measure #1

The percent of eligible payees (Veterans, survivors, and other eligible beneficiaries) that were issued payments

Performance Table

This performance table depicts the percent of economic recovery payments made in each year against the total projected number of payments.

| Results | Targets |
| --- | --- |
| 2009 | 2010 |
| % of Total Estimated ARRA Payments Made | Remaining % of ARRA Payments to be Made |
| 98% | 2% |

Other Required Information

| New or Existing Measure | Results Data Collection Frequency | Public Accessibility Modality | Results Calculation | Results Data Source | Integrated Objective Link | Integrated Strategy Link |
| --- | --- | --- | --- | --- | --- | --- |
| New | Monthly | PAR and/or http:www.va.gov/recovery | The number of ARRA checks issued to Veterans/the number of eligible payees | FMS/ Finance | IO 1: Make it easier for Veterans and their families to receive the right benefits, meeting their expectations for quality, timeliness, and responsive-ness | IS B: Develop a range of effective delivery methods that are convenient to Veterans and their families |

Impact of ARRA on Performance

Payment of the one-time $250 stimulus payment did not impact the delivery of compensation, pension and survivor benefits.

# 8.  Monitoring/Evaluation

Since the one-time $250 payments were made in June 2009, there has been continuous auditing performed to ensure proper payment in the event there were any returned payments or beneficiaries who did not receive a payment.  VA performed a full risk assessment for economic recovery payments, which was discussed in the 2009 Performance and Accountability Report.

# 9.  Transparency

Veterans may call VA’s toll-free telephone number, visit and submit inquiries to VA’s Web site, or visit a regional office to inquire about the one-time payments.

# 10.  Accountability

VA certified entitlement to and receipt of one-time $250 payments and will continue to do so for reissued payments.  An audit and full risk assessment was and will continue to be performed for improper payments.

# 11.  Barriers to Effective Implementation

There are no anticipated barriers to making the one-time $250 payments.

# 12.  Federal Infrastructure Investments

Not applicable

# Appendix

## General Operating Expenses – Support of Veteran Economic Recovery Payments Funding Table

## Table 1A – Account Summary

|  | TAFS (pick from dropdown) | Appropriated to TAFS ($000s) | Program Allocations |
| --- | --- | --- | --- |
|  |  |  | BA Allocation ($000s) | Program Name |
| One account funding one program | General Operating Expenses (36-0150 2009 \ 2010) | 7,100 | 7,100 | GOE Recovery Act |

## Table 1B – Obligations/Gross Outlays – January 2009 through December 2010 ($000)

| Obligations and Gross Outlays, Actuals Through April 2010 ($000s) |
| --- |
| Funding Type | Funding Year | Jan | Feb | Mar | Apr | May | June | July | Aug | Sept | Oct | Nov | Dec |
| Obligation | 2009 |  |  |  | 27 | 794 | 27 | 27 | 27 | 27 | 14 | 14 | 14 |
| Gross Outlay | 2009 |  |  |  | 0 | 96 | 18 | 51 | 0 | 0 | 716 | 19 | 19 |
| Obligation | 2010 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 |  |  |  |
| Gross Outlay | 2010 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 27 |  |  |  |

Note:  Table 1B reflects planned obligations/gross outlays totaling $1.1 million.

## Compensation and Pensions Recovery Act Funding Table

## Table 2A – Account Summary

|  | TAFS (pick from dropdown) | Appropriated to TAFS ($000s) | Program Allocations |
| --- | --- | --- | --- |
|  |  |  | BA Allocation ($000s) | Program Name |
| One account funding one program | Compensation and Pensions (36-0101 2009 \ 2011) | 700,000 | 700,000 | Compensation and Pensions Recovery Act |

## Table 2B – Obligations/Gross Outlays – January 2009 through December 2010

| Cumulative Obligations and Gross Outlays, Actuals Through April 2010 ($000s) |
| --- |
| Funding Type | Funding Year | Jan | Feb | Mar | Apr | May | June | July | Aug | Sept | Oct | Nov | Dec |
| Obligation | 2009 |  |  |  |  |  | 466,288 | 461,310 | 461,449 | 464,812 | 465,092 | 465,231 | 465,168 |
| Gross Outlay | 2009 |  |  |  |  |  | 466,487 | 466,487 | 467,427 | 471,020 | 471,260 | 471,403 | 471,403 |
| Obligation | 2010 | 465,221 | 465,293 | 465,331 | 465,364 | 465,414 | 465,464 | 465,514 | 465,764 | 465,839 | 471,889 | 472,089 | 472,239 |
| Gross Outlay | 2010 | 471,403 | 471,476 | 471,476 | 471,476 | 471,526 | 471,576 | 471,626 | 471,876 | 471,951 | 478,001 | 478,201 | 478,351 |

## Information Technology – Support of Veteran Economic Recovery Payments Funding Table

## Table 3A – Account Summary

|  | TAFS (pick from dropdown) | Appropriated to TAFS ($000s) | Program Allocations |
| --- | --- | --- | --- |
|  |  |  | BA Allocation ($000s) | Program Name |
| One account funding one program | Information Technology – Support of Veterans Economic Recovery Payments (36-0168 2009/2011) | 100 | 100 | VETSNET |

## Table 3B – Obligations/Gross Outlays – January 2009 through December 2010 ($000)

| Funding Type | Funding Year | Jan | Feb | Mar | Apr | May | June | July | Aug | Sept | Oct | Nov | Dec |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Obligation | 2009 |  |  |  |  |  | 100* |  |  |  |  |  |  |
| Gross Outlay | 2009 |  |  |  |  |  |  | 5 | 5 | 5 | 5 | 5 | 5 |
| Obligation | 2010 |  |  |  |  |  |  |  |  |  |  |  |  |
| Gross Outlay | 2010 | 6 | 5 | 5 | 5 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 7 |

# *$100k is the ARRA appropriation amount.  Actual funds spent in 2009 were $243K ($100K ARRA, $143K OI&T).